## Sheet1
Example - Detailed Financial Planning Calendar
Finalize calendar, milestones, deliverables, responsibilities | Finance | Mid-Late Oct
Build financial model in Excel for next fiscal year | Finance | Mid-Late Oct
Build Excel templates to collect department inputs, populated with YTD spending and trendlines | Finance | Mid-Late Oct
Build presentation templates for department review meetings | Finance | 2026-10-27
Build tops-down targets leveraging long range plan | Finance/CEO | 2026-11-02
Determine headcount expense planning guidelines (hiring restrictions, COLA and merit adjustments) | Finance/HR | 2026-11-02
Determine non-headcount expense planning guidelines | Finance | 2026-11-02
Planning Kickoff Meeting; review calendar & roles/responsibilities, distribute templates and guidelines | Finance | 2026-11-05
Review sales AE quota and capacity model to validate revenue targets and determine required staffing | Sales Ops | 2026-11-11
Prepare sales analyses (including product level growth plans) to support ARR plan development | Sales/Sales Ops | 2026-11-11
Cross check ARR growth plan against current pipeline, trendlines, and market | Sales Ops/Finance | 2026-11-11
Preview annual plan targets and planning process with Board | Finance/CEO | 2026-11-16
Proposed ARR monthly plan review with CEO | Sales | 2026-11-18
Financial plan template submissions due to Finance | Dept Leads | 2026-11-27
Review 1st draft consolidated financial plan with CEO | Finance | 2026-11-30
Department reviews with CEO | Dept Leads | 2026-12-01
Determine adjustments necessary to bottoms up plan, considering strategic priorities and tradeoffs | Finance/CEO | 2026-12-04
Review 2nd draft financial plan with CEO | Finance | 2026-12-07
Finalize proposed plan | Finance | 2026-12-08
Pre-vet proposed plan with Board | Finance/CEO | 2026-12-08
Board approval of annual financial plan | Board | 2026-12-15